## Schedule
Domain | Feature | Task | Comment | Priority | Orig. Est. | Curr. Est. | Elapsed | Remain
Users
| Designing database |  |  | 10 | 10 | 10 | 0 | 10
| Creating an account |  |  | 8 | 3 | 3 | 0 | 3
| Removing an account |  |  | N/A |  |  | 0 | 0
| Logging in |  |  | 8 | 3 | 3 | 0 | 3
|  | SSL support |  | N/A |  |  | 0 | 0
| Logging out |  |  | 7 | 3 | 3 | 0 | 3
| Profile (view+edit) |  | Name, lang., etc. | 3 | 5 | 5 | 0 | 5
Total |  |  |  |  | 24 | 24 | 0 | 24
Projects
| Designing database |  |  | 10 | 10 | 10 | 0 | 10
| Creating a project |  |  | 9 | 3 | 3 | 0 | 3
| Removing an existing project |  |  | 1 | 3 | 3 | 0 | 3
| Forum |  |  | N/A |  |  | 0 | 0
| Mailing list |  |  | N/A |  |  | 0 | 0
| Uploading resource file |  | import | 9 | 2 | 2 | 0 | 2
| Removing uploaded file |  |  | 9 | 2 | 2 | 0 | 2
| Downloading locale file |  |  | 7 | 2 | 2 | 0 | 2
| Viewing list of locale files |  |  | 9 | 2 | 2 | 0 | 2
| Assigning remote repository |  | import | N/A |  |  | 0 | 0
| Progress listing |  |  | 7 | 5 | 5 | 0 | 5
| Project members | Add user to project |  | 7 | 2 | 2 | 0 | 2
|  | Remove user from project |  | 3 | 2 | 2 | 0 | 2
|  | Assigning task to user |  | 7 | 3 | 3 | 0 | 3
|  | Unassigning tasks |  | 6 | 2 | 2 | 0 | 2
Total |  |  |  |  | 38 | 38 | 0 | 38
Translatable File Formats
| Architecture design |  |  | 10 | 3 | 3 | 0 | 3
| Portable object (.po) | Reading |  | 9 | 3 | 3 | 0 | 3
|  | Writing |  | 9 | 3 | 3 | 0 | 3
| Java properties | Reading |  | 2 | 2 | 2 | 0 | 2
|  | Writing |  | 2 | 2 | 2 | 0 | 2
| HTML | Reading |  | N/A |  |  | 0 | 0
|  | Writing |  | N/A |  |  | 0 | 0
| XML | Reading |  | 8 | 8 | 8 | 0 | 8
|  | Writing |  | 8 | 8 | 8 | 0 | 8
| DocBook | Reading |  | N/A |  |  | 0 | 0
|  | Writing |  | N/A |  |  | 0 | 0
| Wrapper interfaces to edit |  |  | 9 | 10 | 10 | 0 | 10
[7 empty] | 0 | 0
Total |  |  |  |  | 39 | 39 | 0 | 39
Structured File and Repos
| Architecture design |  |  | 10 | 3 | 3 | 0 | 3
| zip | Reading |  | 7 | 4 | 4 | 0 | 4
|  | Writing |  | 7 | 4 | 4 | 0 | 4
| tar/gzip | Reading |  | 2 | 3 | 3 | 0 | 3
|  | Writing |  | 2 | 3 | 3 | 0 | 3
| CVS repository | Import |  | N/A |  |  | 0 | 0
|  | Sync |  | N/A |  |  | 0 | 0
|  | Push |  | N/A |  |  | 0 | 0
| Subversion repository | Import |  | N/A |  |  | 0 | 0
|  | Sync |  | N/A |  |  | 0 | 0
|  | Push |  | N/A |  |  | 0 | 0
| Wrapper interfaces | for Structured |  | 7 | 5 | 5 | 0 | 5
|  | for Repositories |  | N/A |  |  | 0 | 0
Total |  |  |  |  | 22 | 22 | 0 | 22
Authorization
| Architecture design |  |  | 10 | 3 | 3 | 0 | 3
| Public or private |  |  | N/A |  |  | 0 | 0
| Members to modify |  |  | N/A |  |  | 0 | 0
| Guests to modify |  |  | N/A |  |  | 0 | 0
Total |  |  |  |  | 3 | 3 | 0 | 3
Translation Memory
| Architecture design |  |  | 10 | 3 | 3 | 0 | 3
| Designing database |  |  | 10 | 10 | 10 | 0 | 10
| Licensing |  |  | 4 | 3 | 3 | 0 | 3
| Adding to database |  |  | 9 | 3 | 3 | 0 | 3
| Search related (A) | Naïve |  | 9 | 2 | 2 | 0 | 2
|  | Modified LCS |  | 5 | 3 | 3 | 0 | 3
|  | Researching other algorithms |  | 4 | 10 | 10 | 0 | 10
| Import | TMX |  | N/A |  |  | 0 | 0
|  | XLIFF |  | N/A |  |  | 0 | 0
| Export | TMX |  | N/A |  |  | 0 | 0
|  | XLIFF |  | N/A |  |  | 0 | 0
Total |  |  |  |  | 34 | 34 | 0 | 34
Glossary
| Architecture design |  |  | 10 | 3 | 3 | 0 | 3
| Designing database |  |  | 10 | 5 | 5 | 0 | 5
| Search words | Exact match |  | 9 | 3 | 3 | 0 | 3
| Auto-search | Character- or N-gram-based |  | 8 | 8 | 8 | 0 | 8
|  | Judy array |  | N/A |  |  | 0 | 0
| Suggests highly used |  |  | N/A |  |  | 0 | 0
| Import |  |  | N/A |  |  | 0 | 0
| Export |  |  | N/A |  |  | 0 | 0
Total |  |  |  |  | 19 | 19 | 0 | 19
Editing Interface
| Ajax library |  |  | 9 | 10 | 10 | 0 | 10
|  | prototype.js |  | 8 | 3 | 3 | 0 | 3
|  | Mochikit |  | 8 | 3 | 3 | 0 | 3
| File formats for UI-oriented |  |  | 9 | 10 | 10 | 0 | 10
| File formats for docs-oriented |  |  | 9 | 10 | 10 | 0 | 10
| Suggestions | Translation memory |  | 9 | 8 | 8 | 0 | 8
|  | Glossary |  | 9 | 8 | 8 | 0 | 8
|  | Machine translations |  | N/A |  |  | 0 | 0
| Versioning | Keep tracks of sources |  | N/A |  |  | 0 | 0
|  | Keep tracks of targets |  | N/A |  |  | 0 | 0
|  | Show diff |  | N/A |  |  | 0 | 0
| Co-edting |  |  | N/A |  |  | 0 | 0
Total |  |  |  |  | 52 | 52 | 0 | 52
Internationalization
| Architecture design |  |  | 10 | 3 | 3 | 0 | 3
| Implementation |  |  | 10 | 3 | 3 | 0 | 3
| Japanese localization |  |  | 5 | 2 | 2 | 0 | 2
Total |  |  |  |  | 8 | 8 | 0 | 8
Mailing Notifier
| Architecture design |  |  | N/A
Total |  |  |  |  | 0 | 0 | 0 | 0
Easy Installation |  |  | cf. Xoops
| Architecture design |  |  | 10 | 10 | 10 | 0 | 10
| Implementation |  |  | N/A |  |  | 0 | 0
Total |  |  |  |  | 10 | 10 | 0 | 10
Miscellaneous
| Refactoring |  |  |  | 40 | 40 | 0 | 40
| Debugging |  |  |  | 100 | 100 | 0 | 100
| Testing |  |  |  | 40 | 40 | 0 | 40
| Documentation |  |  |  | 30 | 30 | 0 | 30
| Paperworks |  |  |  | 50 | 50 | 0 | 50
| Buffer |  |  |  | 50 | 50 | 0 | 50
Total |  |  |  |  | 310 | 310 | 0 | 310
Grand Total |  |  |  |  | 559 | 559 | 0 | 559